## Slide 1
Core Principles
Phased Approach: Prioritize automations by complexity, value, and data readiness.
Parallel Tracks: Run discovery/design for multiple automations concurrently.
Agile Sprints: 2-week cycles for rapid prototyping and feedback.
Governance: Weekly steering committee reviews with leadership.
Tooling: Leverage Bunge GenAI, Python, Selenium for speed.
AI Automation Acceleration Program 90-Day AI Automation Plan

## Slide 2
Deploy remaining automations and initiate change management
Deploy automations and initiate change management
Design AI models and develop data pipelines
Finalize scope and assign squads
Validate feasibility and define scope
Phase 3: Testing & Deployment
Week 5-6 Activities
Week 3-4 Activities
Week 11-13 Activities
Phase 1: Discovery & Prioritization
90-Day AI Automation Plan
Week 1-2 Activities
Phase 2: Design & Development
Conduct UAT and deploy Quick Wins
Week 9-10 Activities
Kickoff workshop and AI readiness assessment
Build and test MVPs
Build MVPs and conduct testing
Week 7-8 Activities
Strategic Prioritization
AI Automation Wave 1 (90-Day Focus)
**Quick Wins (Low Effort/High Value)**
✅ TnE - India/BNA/China (PtP)
✅ Cash Application (OtC)
✅ PO Confirmation (PtP)
High Value/Complexity
🔷 Vendor/Customer Master (Master Data)
🔷 Settlements - Rail/Truck/Barge (Customer Svc)
Lower Priority
⏳ Duplicate Audit (Control) *[High Complexity/Low Value]*
⏳ TnE - China (PtP) *[Dependency: Local Compliance]*

## Slide 4: Resource Allocation
Role | Quick Wins | High Complexity
AI Developers (3) | 70% effort | 30% effort
Data Engineers (2) | 50% effort | 50% effort
SME Bandwidth | 5 days/week | 3 days/week
Risk | Impact | Mitigation | Owner
TnE localization compliance | High | Pre-engage legal teams in China/BNA | PtP Lead
Cash app accuracy <85% | Medium | Hybrid human-AI validation layer | OtC Lead
Vendor master data silos | High | Phase 1: Start with SAP-only data | Data Custodian
Risk Dashboard

## Slide 5
Tower | Automation | Day 30 (Scope) | Day 60 (MVP) | Day 90 (Status)
OtC | Cash Application (Global) | ✅ Scope | ✅ MVP Tested | 🚀 Deployed
Master Data | Vendor/Customer Master | ✅ Scope | ✅ MVP Built | 🚀 Deployed
Customer Service | Rail Settlement (EGT/OPD/Eastern rail) | ✅ Scope | ⏳ Dev | 🚀 Deployed
Customer Service | Truck Settlement (EGT/OPD) | ✅ Scope | ⏳ Dev | 🚀 Deployed
Customer Service | Barge Settlement | ✅ Scope | ⏳ Dev | 🚀 Deployed
Customer Service | Quality; Address Verification | ✅ Scope | ⏳ Dev | 🚀 Deployed
Customer Service | Supply Chain; Shipment Creation | ✅ Scope | ✅ MVP Built | ⚙️ UAT
Customer Service | Supply Chain; Outbound Shipment | ✅ Scope | ⏳ Dev | 🚀 Deployed
Control | Transaction Audit | ✅ Scope | ⏳ Dev | 🚀 Deployed
Control | Duplicate Audit | ✅ Scope | ✅ MVP Tested | 🚀 Deployed
PtP | Single Line Invoice(BNA) | ✅ Scope | ✅ MVP Tested | 🚀 Deployed
PtP | PO Confirmation (BEMEA+BNA) | ✅ Scope | ✅ MVP Tested | 🚀 Deployed
PtP | TnE - India | ✅ Scope | ⏳ Dev | 🚀 Deployed
PtP | TnE - China | ✅ Scope | ✅ MVP Built | ⚙️ UAT
Automation Delivery Schedule
Legend: ✅ = Complete, ⏳ = In Progress, 🚀 = Deployed, ⚙️ = Testing
Updated Delivery Schedule (Post-Prioritization)

## Slide 6
90-Day Outcomes & ROI
✅ 12 automations LIVE: TnE (India/BNA), Cash App, PO Confirmations, Invoice Processing
➡️ Efficiency Gains: 50% FTE reduction in PtP/OtC
⚠️ De-risked: Vendor Master / Customer Master Changes Phase 1 (SAP-only)
📅 Next Wave: Customer Service - Supply chain by Day 120
By focusing on quick wins first, we deliver ~$200K annual savings by Day 90 with minimal risk
Executive Summary

## Slide 7
90-Day Plan: High-Level Timeline
Phase 1: Discovery & Prioritization (Days 1-30)
Goal: Validate feasibility, define scope, and secure resources.
Key Activities:
  Week 1-2:
    Kickoff workshop with tower leads to map processes, pain points, and data sources.
    AI Readiness Assessment: Data quality checks (e.g., format, completeness) for all automations.
    Prioritize automations using Value vs. Effort Matrix:
  Week 3-4:
    Finalize automation scope and success metrics (e.g., FTE reduction, error rate improvement).
    Assign dedicated squads (Process Owner + Data Scientist + Developer).
    Leadership Checkpoint: Present prioritization, ROI estimates, and resource plan.
Phase 2: Design & Development (Days 31-60)
*Goal: Build and test MVPs for 4-5 automations.*
Key Activities:
  Week 5-6:
    Sprint 1: Design AI models (e.g., NLP for invoice processing, ML for cash matching).
      Focus: OtC Cash Application, Duplicate Audit, PO Confirmation.
    Develop data pipelines (APIs, ETL) and integration hooks (ERP, SAP).
  Week 7-8:
    Sprint 2: Build MVPs for prioritized automations.
      Focus: Vendor Master Creation, TnE - India/BNA.
    Conduct unit testing and peer reviews.
  Leadership Checkpoint: Demo MVPs; share early results (e.g., 70% accuracy in cash matching).
Phase 3: Testing & Deployment (Days 61-90)
Goal: Deploy 3 automations; others in UAT.
Key Activities:
  Week 9-10:
    Sprint 3: User Acceptance Testing (UAT) with business teams.
      Refine models based on feedback (e.g., handle invoice exceptions).
    Deploy Quick Wins:
      OtC Cash Application (Global),
      Duplicate Audit (Control),
      PO Confirmation (PtP).
  Week 11-13:
    Sprint 4: Deploy remaining Wave 1 automations (Vendor Master, TnE-India).
    Initiate change management (training, documentation).
    Leadership Checkpoint: Review deployment results, lessons learned, and Wave 2 plan.

## Slide 8
AI Automation 90-Day Plan - PowerPoint Template
Slide 1: Title Slide Title: AI Automation Acceleration Program Subtitle: 90-Day Implementation Roadmap Visual: Modern tech background with AI/automation imagery Content:
Presenter: [Your Name]
Date: August 2025
"Delivering intelligent automation across 7 functional towers"

## Slide 9
Slide 2: Strategic Prioritization Title: Focus Areas for Maximum Impact Visual: Priority matrix with icons
[QUICK WINS] [HIGH VALUE/COMPLEX] [LOWER PRIORITY]
┌─────────────────┐ ┌──────────────────┐ ┌────────────────┐
│ ▣ TnE India │ │ ▣ Vendor Master │ │ ▣ Duplicate │
│ ▣ TnE BNA │ │ ▣ Settlements │ │ Audit │
│ ▣ TnE China │ │ (Rail/Truck) │ │ (High Comp/ │
│ ▣ Cash App │ │ ▣ Billback │ │ Low Value) │
│ ▣ PO Confirmation│ └──────────────────┘ └────────────────┘
└─────────────────┘
Key:
Quick Wins: Low Effort + High Value (70% team focus)
High Value/Complex: Strategic but resource-intensive (25% focus)
Lower Priority: Deferred to Wave 2 (5% discovery on

## Slide 10
Slide 3: 90-Day Roadmap Title: Execution Timeline Visual: Gantt chart (copy-paste this Mermaid code):

## Slide 11
Slide 4: Resource Allocation Title: Team Structure & Focus Visual: Donut chart + role matrix
[Resource Distribution]
🟢 Quick Wins: 70%
🔵 High Value: 25%
⚪ Other: 5%
[Team Structure]
┌──────────────────┬─────────────────────────────┐
│ Role │ Allocation │
├──────────────────┼─────────────────────────────┤
│ AI Developers │ 3 FTEs (Focus: TnE, Cash) │
│ Data Engineers │ 2 FTEs (Vendor Master) │
│ Process SMEs │ 1 per tower (Rotation) │
│ Program Manager │ 1 (Overall coordination) │
└──────────────────┴─────────────────────────────┘

## Slide 12
Slide 5: Risk Dashboard Title: Proactive Risk Management Visual: Color-coded risk matrix
┌──────────────────────────────┬───────┬──────────────────────────────────┬───────────┐
│ Risk │ Level │ Mitigation Strategy │ Owner │
├──────────────────────────────┼───────┼──────────────────────────────────┼───────────┤
│ TnE compliance issues │ 🔴 High│ Pre-engage legal teams in-region│ PtP Lead │
│ Cash app accuracy <85% │ 🟠 Medium│ Hybrid validation layer │ OtC Lead │
│ Vendor data silos │ 🔴 High│ Phase 1: SAP-only implementation│ Data Steward│
│ SME bandwidth constraints │ 🟠 Medium│ Dedicated SME days per tower │ Program Mgr│
└──────────────────────────────┴───────┴──────────────────────────────────┴───────────┘

## Slide 13
Slide 6: Delivery Status Title: Day 90 Deployment Tracker Visual: Status table with RAG indicators
[Day 90 Outcomes]
▸ 3 automations in production
▸ $850K annual savings identified
▸ 55% FTE reduction in PtP processes
▸ 68% error reduction in cash application
[ROI Projection]
Year 1: $1.2M savings
Year 2: $2.8M savings
┌───────────────┬──────────────────────────────┬───────────────────┬────────────┐
│ Tower │ Automation │ Status │ Target │
├───────────────┼──────────────────────────────┼───────────────────┼────────────┤
│ 🟢 PtP │ TnE - India/BNA/China │ 🚀 Live │ Day 80 │
│ 🟢 OtC │ Cash Application (Global) │ 🚀 Live │ Day 85 │
│ 🟢 PtP │ PO Confirmation │ 🚀 Live │ Day 75 │
│ 🟡 Master Data│ Vendor Master Creation │ ⚙️ UAT │ Day 90 │
│ 🟠 Customer Svc│ Billback Settlements │ ✅ MVP Ready │ Day 90 │
│ ⚪ Control │ Duplicate Audit │ ⏳ Design Phase │ Wave 2 │
└───────────────┴──────────────────────────────┴───────────────────┴────────────┘

## Slide 14
Slide 7: Metrics & ROI Title: Tangible Business Impact Visual: Performance dashboard
[Day 90 Outcomes]
▸ 3 automations in production
▸ $850K annual savings identified
▸ 55% FTE reduction in PtP processes
▸ 68% error reduction in cash application
[ROI Projection]
Year 1: $1.2M savings
Year 2: $2.8M savings

## Slide 15
Slide 8: Next Steps Title: Beyond 90 Days Visual: Roadmap illustration
Wave 2 (Next 90 Days):
1. TnE China deployment
2. Settlements automation (Rail/Truck)
3. Vendor Master global rollout
4. Billback implementation
Strategic Expansion:
▸ GenAI for complex decision support
▸ Cross-tower automation orchestration
▸ Real-time analytics dashboard